## CoE
Duration | Task | Owner | Comments
Week #02
2011.09.28 - 2011.09.30 | Application code review - Front-end | Bijesh | Optimization toward 8 developers Gavin gather all ready sources from all develolpers for review Gavin confirm the document of 1st set of improvement with Bijesh Gavin implment general improvement on 8 developers' resource Bijesh help to check the sources to see any other places to improve and advise
| Application code review - Back-end | Srinivas | Gavin brief backend to Srinivas Backend resources already provided to Srinivas by MA Bo on Sep.27
| Integration testing issue support | Bijesh Srinivas
Week #03
2011.10.03 - 2011.10.05 | Development Server upgrade | Bijesh Srinivas | Upgrade from FP1 CU4 to FP1 CU5
| Test Server upgrade | Bijesh Srinivas | Official national day holidays for local team, WANG ZhiQiang provide on-demand support
| Upgrade validation | Bijesh Srinivas | 13816721226 / wangzhiqiang@cordys.com.cn
Week #04
2011.10.08 | Application code review - Front-end | Bijesh | Optimization toward 8 developers Gavin implment general improvement on 8 developers' resource Bijesh help to check the sources to see any other places to improve and advise
| Application code review - Back-end | Srinivas | Optimization toward 8 developers Srinivas provide advise on typical backend source code Gavin implment general improvement on 8 developers' resource Srinivas help to check the other sources to see any other places to improve and advise
2011.10.09 | Production server installation |  | HA environment setup with FP1 CU5
| Production server optimization |  | Involve R&D performance team if necessary
| Integration testing issue support | Bijesh Srinivas
Week #05
2011.10.10 | Production server installation | Bijesh Srinivas | HA environment setup with FP1 CU5
2011.10.11 - 2011.10.14 | Production server optimization | Bijesh Srinivas | Involve R&D performance team if necessary
| Application code review - Front-end | Bijesh | Optimization toward 8 developers Gavin implment general improvement on 8 developers' resource Bijesh help to check the sources to see any other places to improve and advise
| Application code review - Back-end | Srinivas | Optimization toward 8 developers Srinivas provide advise on typical backend source code Gavin implment general improvement on 8 developers' resource Srinivas help to check the other sources to see any other places to improve and advise
| Production server optimization |  | Involve R&D performance team if necessary
| Test server optimization | Bijesh Srinivas | Involve R&D performance team if necessary
| Database server optimization | Bijesh Srinivas | Involve R&D performance team if necessary
| Load testing support |  | Optimization toward 200 concurrent users (to be confirmed) LoadRunner be used for load testing
| UAT issue support | Bijesh Srinivas
Week #06
2011.10.17 - 2011.10.21 | Load testing support | Bijesh Srinivas | Optimization toward 200 concurrent users (to be confirmed) LoadRunner be used for load testing
| Production server optimization | Bijesh Srinivas | Involve R&D performance team if necessary
| UAT issue support | Bijesh Srinivas
Week #07
2011.10.24 - 2011.10.28 | UAT issue support | Bijesh Srinivas | Will go live on 2011.11.03
| Go-live support | Bijesh Srinivas
| Wrap up | Bijesh Srinivas
Comments
Application UI response time target: 3 seconds
The optimization tasks should include (not limited to)
・ Cordys server optimization for DTAP
o Product
§ BPM
§ XForm
§ WS-AppServer
o Apache
o OS
・ Application optimization
o BPM
o XForm
o WS-AppServer
・ Database server optimization
The availability of Bijesh is subject to change as per visa extension status