## TechnicalDesign
Reg. No | Requirement Briefing | Priority | Requirement Details | Owner | Support
T-BPM-TD-001 | Set the duration of the activities dynamically | 4 | 20110726(mabo) 1. in T-BPM project, most human activity have the same duration, but some human have the special duration,how can set the activity duration easily in the same configuration ways(mabo).
T-BPM-TD-002 | We need to monitor, using BAM component, the Business Data along with the process data | 4 | 1. we now have the requirement, to show the manager level, the quantity of the timeout activities, the user can drill down by department,or regional Sub Company.in the final , the user can see the activity which is timeout by process instance graph and the activity should be in red corlor(mabo) 2. based on designed KPI
T-BPM-TD-003 | Status level monitoring is needed for each activities | 3 | 20110726(mabo) 1. there is a drilldown requirement . And the customer can show the status level of the different BPM(not the Cordys BPM, should be the business definition)
T-BPM-TD-004 | Need the best performance results (displayed in 3 seconds) for the most complex User Interface (Target Shop SurVey) | 5 | 1.Database integration: business data will be persisted in database and displayed in the frontend 2.SAP integration a.Consideration of migration to PI in the future b.Common and relatively static data from SAP which is used in UI (like select box data) will be sychronized to our local DB on daily basis to avoid querying the SAP for common data, but still the performance should be considered like front end caching and related cache update mechanism | Lakshman | JIANG QingRong
T-BPM-TD-005 | Better UI design is also required for the above said XForm | 1 | 20110726(mabo) 1. good customer feeling. And easy to use.
T-BPM-TD-006 | The style sheet of all the User Interfaces should be similar to the customer's portal style | 2 | 20110726(mabo) 1.we need intgrate with EIP (portal) , and the portal have the different styles. So we need adjust the cordys css to mapping the portal styles.(mabo)
T-BPM-TD-007 | Error handling for SAP | 3 | 2. retry mechnism(According the different error information, the system can have retry mechnism,such as connect error. but some error cant retry ,such as data format error.)
T-BPM-TD-008 | Each transactions to the SAP should be logged in our layer and it should be shown in our area for development and debugging For the development and debugging perspective, all the request and responses (which are required) to be logged. The following categories are important 1. SAP Communication error infos 2. All the transactions of SAP, Hisense (name may not be correct) and TAM 3. All the SAP error codes should be converted into respective error details for the easy understanding | 4 | 20110726(mabo) 1. issue follow up. If error occurred when invoking the interface. The customer should know the error information. 2. SOAP request and response should be recorded(mabo)
T-BPM-TD-009 | Translations is important. These translations should be there for even Cordys notifications headers as well | 2 | 20110726(mabo) 1. translation is only translate some Cordys Page into chinese. It's good user feeling.
T-BPM-TD-010 | Integration with EIP system (Not much of importance as of now) | 4 | 20110726(mabo) 1. if the T-BPM integrate with EIP, the EIP should access CORDYS via URL
T-BPM-TD-011 | Integration of organization structure modeled in the organization model with BPM, XForm and EIP | 5 | 1.Visibility of the organizational model to BPM/XForm a.Display the hierarchical page for end user to select b.Share the user interface among different organizational units c.Shall we define two set of roles, one is functional roles used in BPM/XForm, another is corresponding to organizational structures d.after completing the current activity, the next activity should be assigned to the current user's manager or other user as per business scenario e.Control the usability(visible/invisible/readonly) as per the organizational structure 2.Share the same model among different sub companies and headquarters 3.Integration with EIP a.Synchronize users data into Cordys b.Synchronize organizational structure data into Cordys (generate the organzational model automatically) c.Assign roles to user automatically | Saravana | MA Bo
T-BPM-TD-012 | SSO implementation with TAM model | 5 | HTTP Header integration vs Form integration | ZHANG LiQiang | HOU Gang
T-BPM-TD-013 | As of now Inbox is showing few attributes, there is a requirement to show more attributes in that. This may be custom or standard attributes | 3 | 20110726(mabo) 1. there is also a requirement for task query. The user should have some query conditions(such as process name, or some business data) to get the data task. local validation
T-BPM-TD-014 | The User Interfaces should have access restrictions. Only certain users + the user who initiated the BPM should be able to open certain User Interfaces | 3 | 20110726(mabo) 1.the user who initiated the BPM and who has been invovled in the process instance should be able to see the UI.
T-BPM-TD-015 | Data base design of business (Target Shop SurVey) | 5 | 1.Identify the list of tables for their corresponding Xform mapping 2.Identify the primary key(s) and relational key(s) between the tables. 3.Confirm the data types of the columns, before generate the web services. 4.Auto increment(database generated) fields should be identified 5.Should follow the case sensitive rules for database creation(UPPER CASE). | JIANG QingRong | MA Bo
T-BPM-TD-016 | Adding INSTANCE_ID in the ATTACHMENT and APPROVAL tables | 5 |  | JIANG QingRong
T-BPM-TD-017 | Formatting the Input messages for Main and Sub processes | 5 |  | Saravana | Kun Dai
Note on C1: Kun Dai: 1 low 2 3 4 5 critical
Note on B3: Kun Dai: based on designed KPI
Note on B8: Kun Dai: PI
Note on B14: Kun Dai: local validation